## Slide 1
Program Title
Air Force Review Board (AFRB) Date
Rank, Name
Office Symbol
Date
Milestone B Template
See Notes Pages
for additional
information
CLASSIFICATION/FOR OFFICIAL USE ONLY/Pre-Decisional/AFRB (or DAB) Support
CLASSIFICATION/FOR OFFICIAL USE ONLY/Pre-Decisional/AFRB (or DAB) Support
This template is for guidance only
and is not mandatory.
Examples are for illustrative purposed only
Notes: To schedule a HQS AFRB please contact the AFRB Secretariat (SAF/AQXE): Mr Stan Armstead at 571-256-1804 or Major Bryan Lowe at 571-256-0407. The earlier you request a meeting the more likely you will get the dates you need.
AS A REMINDER CHARTS ARE DUE TO THE SECRETARIAT 7 DAYS AHEAD OF THE BRIEFING OR THE MEETING MAY BE CANCELLED.
The purpose behind this template is to provide guidance on the issues and requirements to address at MS B. Each briefing will be different depending upon the nature of the program. Only brief those items that are important for the MDA to make a decision. All briefings should have less than 40 charts (not counting back-ups) to be briefed to SAF/AQ within the one hour and one-half hour that will be scheduled for the meeting.
If you have questions in preparing your briefing please contact your local Acquisition Center of Excellence (ACE) for guidance.
  Wright Patterson AFB DSN: 785-5494/COMM: 937-255-5494
  Hanscom AFB DSN: 845-1660/COMM: 781-225-1660
  Eglin AFB DSN: 875-0526/COMM: 850-883-0526
  Warner Robbins DSN 468-0274/COMM: 478-926-0274
Hill AFB DSN: 777-7999/COMM: 801-777-7999 or-777-5538
Tinker AFB DSN: 884-2791/COMM: 405-734-2791
  Los Angeles AFB (SMC/PID) DSN: 633-1534/COMM. 310 653-1534
  SAF/AQXE Commercial: 571-256-0352 (If you have recommendations to improve the template)
Pls mark documents as follows for ACAT I programs going to OSD per OSD/GC recommendations "CLASSIFICATION/FOR OFFICIAL USE ONLY/Pre-Decisional/DAB Support."

## Slide 2: Briefing Outline – Key Items
BLUF
Program Description/Overview
CONOPS
Requirements
Interrelationships
MS B Affordability
  Portfolio Perspective
  APB--KPPs
  Affordability Template
  Tradeoffs
Product Support Quad Chart
Schedule
Business Strategy
  Production Rate
Funding
Program Risk and Risk Mitigation
Document Status
Exit Criteria
Recommendations for ADM
Way ahead
Back-up
  Program Office Resources, Technical and Systems Engineering Assessment, Test and Eval
  Other (e.g.., open actions from previous ADMs, Congressional concerns/funding cuts, industrial base issues, spectrum considerations, etc.)
Notes: While it is not mandatory, nor possible, in an hour and a half to address all the subjects, it is prudent to be prepared to brief or address all topics.

## Slide 3: Bottom Line Up Front (BLUF) (Decisions Requested & Key Program Info
Purpose
  Present Way Ahead for Program
  Discuss oversight and management plan for Program
Decisions you are requesting (examples)
  Approval Milestone B (if AF is MDA)
  Approval to award contract
  Approval to proceed to OIPT and DAB (if OSD is MDA)
  Obtain SAE approval program baseline/way ahead
  Approve Applicable delegations/waivers (e.g., 2366b waiver)
List Outstanding Issues
  Issue 1--CAPE estimate is double current budget
  Issue 2--TRL level 5 for one of 6 critical technologies

## Slide 4: Program Description/Overview
Description
Acquisition Strategy
  Evolutionary Acquisition
  Competitive Risk Reduction / Source Selection
    Raytheon Missile Systems, Tucson
    The Boeing Company, St Louis
  EMD-Fixed-Price Incentive Firm Target (FPI(F))
  Production
      Lots 1-3 -- FPI(F)
      Lots 4-5 – Fixed-Price NTE w/ Economic Price Adjust
  Phase Verification:
      Phase I—F-15E Normal attack
      Phase II—F-15E CAM/SAL
      Phase III—F-35B and F-35C Integration
Spectrum Supportability Risk Assessment Status
Equipment Spectrum Certification Stage
  250-lb Class, Precision Guided, Air-to-Ground Munition
  Kill Mobile and Fixed Targets Through Weather from Standoff
  Uses Tri-Mode Seeker & Dual-Band Data Link (Link 16 + UHF)
  Services: USAF, DoN
  Threshold Platforms: AF--F-15E; USMC--F-35B; USN--F-35C
  IMD sensitive (for clarification see notes)
  ACAT Level: ID
  MDA: USD (AT&L)
  PEO:
  PM:
Schedule
Approved Funding
Notes: Intelligence Mission Data (IMD). DoD intelligence used for programming platform mission systems in development, testing, operations, and sustainment including, but not limited to, the functional areas of signatures, EWIR, OOB, C&P, and GEOINT.
IMD-dependent programs. Any acquisition programs that will require IMD (e.g., programs that carry out combat identification, ISR, and targeting using, but not limited to, signatures, EWIR, OOB, C&P and GEOINT.)

## Slide 5: Requirements
Operational Requirements
  When Approved (AOA, ICD/CDD/CPD, CONOPS)
  Key KPPs—fully identified and clearly stated?
  Incremental Requirements?
    All increments contained in one CDD?
    EMD phase for each increment planned for 5 years or less?
  How will program achieve information assurance requirements? (see footnotes)
Operational Capabilities/Impacts
  Capabilities / missions (today & future)
    Relationship to established roadmap(s) / architecture(s)
    Family of Systems (FOS) / System of Systems (SOS) / Complementary Systems
      Example for E-10A: MP-RTIP, Global Hawk, MP-CDL
AFSPC/AFMC Attestation Statement (See notes)
(See Notes for SSRA/ESC)
Notes: This particularly import for Command, Control, Communications, Computers, Intelligence, Surveillance, and Reconnaissance systems; and information technology programs that depend on external information sources or provide information to other DoD systems.
MAJCOM Attestation Statement (Provided by AFMC/A5C or AFSPC/A5C). See AFI 63-101: Both AFSPC and AFMC will attest that the capability requirements as described in all CDDs…are feasible. If appropriate, attestation will be completed concurrent with document presentation to the AFROC.
DoDI 4650.01 page 12 covers Spectrum Supportability Risk Assessment. Consider Spectrum Supportability Risk Assessment Status and Equipment Spectrum Certification Stage (SSRA/ESC) impact on requirements.

## Slide 6
Concept of Operations

## Slide 7: Interrelationships, Dependencies & Synchronization with Complementary Systems
Mission Planning
PFPS
JMPS
Aviation Platforms:
KC-135
KC-10
AWACS
H/MH-60
CV-22
MH-47
MH-6
CH-53
A/OA-10
LAIRCM
Ground Teams:
GAWS
SF
SEAL
STS
HC/MC-130 Recap
No known issues affecting inter-related programs
Resolvable interface issues affecting programs
Unresolvable interface issues affecting programs
Solid denotes current system
Dash denotes future system
Arrow to Recap denotes supports Recap
Arrow from Recap denotes Recap supports
Indicates program are interdependent
C-130J:
Aircraft Procurement
& Block Upgrades
Be sure to include CYBER links and infrastructure. Indicate any issues/cybersecurity risks introduced by program interconnection.
Notes: Purpose:
  Very few programs today operate or function independently. Most programs are affected by other components and systems, and it usually takes a combination of programs to accomplish the full effects of a weapon or communication system. The Program Manager of the reviewed program is the best source of information on which programs/systems the reviewed program depends upon either operationally (supports other weapon systems), physically (embedded components) or systemically (communications or digital links).
Business Rules: a. Programs to Include: The reviewed program is in the center of the chart with any crucial interrelated programs, including communication links and cyber infrastructure, listed with arrowheads denoting the direction of dependency. Crucial interdependencies are such that the program under review cannot achieve capabilities articulated in the CONOPs, CDD, or CPD (as appropriate) without the related capability provided by this program. Two way dependencies will have a double-headed arrow. Program groupings, where possible, should be by mission or capability area vice platform type. Include programs currently in development. b. Availability: Indicate whether the deliverables from one program to the other are on track, both in quantity and in schedule. If either of the interrelated programs are at risk of missing giver-receiver dates, color the interdependency arrow red or yellow for the appropriate severity. Be prepared to discuss reason for delay, impact, and mitigation. c. Interoperability: Indicate whether the technical performance requirements are being met by the interrelated programs such that they will be able to integrate and function together. Assess both hardware and software/data interoperability. If there is a risk or issue affecting the interoperability of the systems, color the interdependency line red or yellow for the appropriate severity. Be prepared to discuss interoperability issues, impact, and mitigation. d. Security: While systems may be available and interoperable, there may exist security risks to the Reviewed program or due to the interconnection with the crucial interrelated programs identified. Consider all areas of security that result in overall mission risk, including: Personnel Security, Physical Security, Software Assurance, Cybersecurity, Supply Chain Risk Management, Anti-Tamper, Industrial Security, Operations Security, and Communications Security. Color the interdependency line green, yellow or red for the appropriate risk level. Be prepared to discuss moderate/high risks, impact, and mitigation.

## Slide 8
Why they matter. . .
See Notes Page
APB Key Performance Parameters
Consider SSRA and ESC status.
Notes: 8
What matters:
Top KPP/KSAs that are the primary drivers of cost, schedule, and risk for this program
Requirements that are the most significant drivers of technical and schedule risk

## Slide 9: Affordability
MS B Affordability Goal: ?
MS B APB APUC Objective: ?; APB Threshold: ?
  Estimated APUC at ?
Two Affordability changes are drafted in the (Specify Milestone) ADM
  Reflect the APUC Affordability Goal at ?% above APUC objective ($?)
Are there Cost Affordability Drivers?
  If so, please explain.
Are there any disconnects throughout the lifecycle?
  How will the disconnects be addressed?
Are there any Schedule drivers impacting the Affordability Goal?
  If so, please explain.

## Slide 10
Affordability Requirement
Description | Affordability Requirement (MS ? ADM) BY?? | Dec 17 SAR (In DAMIR) BY??: $? | Service Cost Position Estimate (23 Oct 18) BY??: $??
APUC (Note 1) | $? | $? | $?
O&M | $?/Unit | $?/Unit | $?/Unit
Note 1:
Quantity
APB APUC Objective $?
APB APUC Threshold $?
Notes: Affordability Template MS C (Single Quad Chart)
Purpose: Provide the Affordability Requirements and amplify information on RDT&E and Procurement learned during design trades.
Top left quadrant: Display proposed Affordability Requirements for MDA approval. In most cases these will be the same areas used as Affordability Targets from MS A, updated to reflect the results of affordability decisions made since that time. These will be precise expressions of cost and schedule to be controlled and should have been weighed objectively for both front-end unit cost and long-term ownership cost, and be based on engineering analysis. The PM should be prepared to explain why any elements from MS A/B were not selected for MS C, or any new elements added for MS C.
Top right quadrant: Provide results of the most significant trade studies addressing Affordability Drivers. First row should be the baseline estimate of each cost element from MS A, subsequent rows should show “delta” effects of each trade study on the cost elements. The bottom row should show a current estimate, which should include but not be limited to, the info in the table. (Because not all trades can be shown in the table, the columns may not add correctly. However, if the chart shows the most significant results they should not be excessively out of line.) The current estimate should be consistent with budget information shown elsewhere in the briefing deck.
Bottom:
Discussion points.

## Slide 11: Program Requirements
Top Requirements Cost Drivers
Performance (KPPs & select KSAs)
KPP 1
Extended Range
KPP 2
MME
KPP 3
Mat. Availability*
KPP 4
Net Ready
KSA 1
Reliability
N
T
O
Technology Readiness Assessment
N – No Capability
T – Threshold
O - Objective
Critical Technologies | To Date | Est. @ FRP
Engine | 8 | 9
Engine Lube System | 8 | 9
FMU 156/B Fuze | 9 | 9
Low Observable | 7 | 7*
GPS | 7 | 7*
MS B Date: N/A
MS C Date: Oct 10
* Analysis
Acquisition Program Baseline (APB)*
Schedule
- MS C
- Assets Avail.
Cost
PAUC
+10%
+15%
$1.1M
Baseline (O)
$1.21M
$1.265M
(O) Sep 10
(T) Dec 11
(O) Apr 13
(T) Apr 14
G
G
* Based on proposed APB
* Due to testing constraints
Cost
APUC
+10%
+15%
$1.1M
Baseline (O)
$1.21M
$1.265M
G
G
TRLs meet LRIP entrance criteria
Notes: Top Cost Driver:
Identify the top 5 or so areas that drive current program costs and their percentage of total program Acquisition Costs.
The 5 or so areas combined should represent at least 75% total program costs.
Performance (KPPs & select KSAs)
The actual Objective and Threshold values from the APB will be added in place of the “T” and “O”.
The arrow locations and color are based on the PMs current estimate.
Placement of the arrow reflects current status of the TRL that best supports obtaining the Threshold/Objective value of the KPP/KSA (i.e., a KPP/KSA with supporting TRL of 6 or below will be positioned to the left of the Threshold value, and will vary depending on how close the TRL is to achieving 7 or better.
  Use Red to indicate that the KPP Threshold value cannot be achieved without reaching or exceeding 10% of the APB Cost Baseline or exceeding 6 months from the APB Schedule Baseline.
  Use Yellow to indicate that there is risk of not meeting the KPP threshold & identify, on a separate chart, the corrective actions taken.
  Use Green to indicate that KPP Threshold has been achieved or is on a path to be met within current APB Cost and Schedule baselines.
The intent is not to list every KPP or attribute. However, should include, at a minimum the KPPs and KSAs associated with cost, schedule or technology challenges. Add the KPP/KSA title under the KPP/KSA number listed
Technology Readiness Assessment
Identify the critical technologies for the program.
Provide the SPO estimated TRL assessment for the Next Major Milestone (consistent with the MS chosen for the APB Schedule section).
Acquisition Program Baseline
Input the Objective Cost or Schedule from the APB in place of “Baseline”. If there is no APB, so state; however, provide program office estimated baseline information.
The arrow location and color are based on the PMs current estimate.
  Use Red to indicate that the Cost/Schedule values will reach/exceed 10% of APB Cost Baseline or 6 months from APB Schedule Baseline.
  Use Yellow to indicate that there is risk of reaching or exceeding 10% of the APB Cost Baseline or 6 months from the APB Schedule Baseline and identify, on a separate chart, the corrective actions taken to correct.
  Use Green to indicate that Program capabilities will be delivered within the APB Baseline Cost and Schedule.
Identify the APB’s Objective Cost, Program Acquisition Unit Cost (PAUC) & Average Procurement Unit Cost (APUC) for the program.
Identify either the Objective IOC or FOC values which ever is next.
Identify the + 10% and + 15% values from the APB Cost Baseline Values.
Identify the +6 months and +9 months values from the APB Schedule Baseline Values.
The next major program event will be identified (MS A/B/C, PDR, CDR, DT/OT, OPEVAL, FIRST FLIGHT, ETC)
Provide MS B and C Dates in box indicated.
Attestation Statement
This chart along with the PM of Record signed Requirements Feasibility Assessment Memo provides information necessary for AFMC/CC’s Attestation stated on the Requirements Chart in this briefing.

## Slide 12: Technology Readiness
Critical Technology Element | TRL | Incr 1 | Incr 2
 | 9 | X | 
 | 6 |  | X
 | 9 | X | 
 | 8 | X | 
 | 9 | X | 
 | 9 | X | 
 | 7 |  | X
 | 5 |  | X
 | 6 |  | X
 | 6 |  | X
 | 9 | X | 
 | 6 | X | 
 | 9 | X | 
 | 8 | X | 
 | 8 | X | 
Technology Readiness Levels (TRL)
See Notes Page
Notes: List key program technologies; current TRLs. TRL 6 is required by MS B. If a technology is below TRL 6 summarize the technology maturation approach (pre-MS A) or summarize the verification of the technology maturation (pre-MS B/C)
List TRL level for critical technologies which may impact meeting a KPP , KSA or APA thresholds or represent risk to deliver capability on schedule and budget
Recommend explaining maturity plans for any CTEs that are not at the requisite level when the review takes place (i.e. TRL 6 at MS B, TRL 7 at MS C).
The category of Technology identifies the key technologies necessary for this program. Column 2 the TRL and the next two columns in this sample (showing two increments) provides the increment in which the technology will be delivered.
This sample generally applies to hardware
Additionally you may want to utilize the Technology Development and Transition Strategy (TDTS) Guidebook, which can be found at the DAU website.
(See OSD AS Template para 6.3)

## Slide 13: Milestone B Cost Capability Analysis
Strategy for finding the right balance between operational capability and affordability
  What technologies/risks were examined to explore trade space between operational capabilities and cost?
    If the key trades are technical, what are those elements around which some “sweet spots” can be influenced?
  Discuss how cost capability analysis was used to determine final threshold/objective values
  Which requirements were the most costly or risky?
  Which requirements could result in cost savings if adjusted?
  Was there a knee in the cost capability “curve” for the most costly and or risky requirements?
  How have affordability goals and constraints been included in the program and how will they be achieved?
  Impact of procurement rate (EOQ) and schedule impact on affordability target.
SEE NOTES PAGE
Notes: Worksheet for trades found in backup.
See also slides 41 and 42 for alternative methods of presenting

## Slide 14
Product Support Strategy
Metric | Antecedent Actual | Original Goal | Current Goal | Current Estimate/ Actual
Materiel Availability | 76% | 80% | 77% | 71%
Materiel Reliability | 37 hrs | 50 hrs | 50.5 hrs | 48 hrs
Ownership Cost | 245.6B | 385.5B | 395.1B | 395.1B
Mean Down Time | 12 hrs | 20 hrs | 18 hrs | 15 hrs
Metrics Data
* Test or fielding event data derived from _______
Sustainment Schedule
O&S Data
MS B
MS C
IOC
FRP
FOC
Sustainment
BCA
LCSP
CLS Start
Depot Standup
LRIP Contract Award
Blended Partnership Startup
PBL Recompete
Avionics PBL
PBL Recompete
Sustainment Approach
  Current (initial CLS covering total system)
  Future (sub-system based PBL contracts)
Issues
  Shortfall in O&M funding in FYDP
  Reliability and availability estimates are below goals
  LCSP requires update before DAB
Resolution
  POM request for O&M restoration submitted
  Reliability improvement plan with clear RAM goals up for final signature
  LCSP in draft
BCA
BCA
BCA
Cost Element | Antecedent Cost | ABC Original Baseline | ABC Current Cost
1.0 Unit-Level Manpower | 3.952 | 5.144 | 5.750
2.0 Unit Operations | 6.052 | 6.851 | 6.852
3.0 Maintenance | 0.739 | 0.605 | 0.688
4.0 Sustaining Support | 2.298 | 2.401 | 2.401
5.0 Continuing System Improvements | 0.129 | 0.025 | 0.035
6.0 Indirect Support | 1.846 | 1.925 | 1.956
Total | 15.046 | 16.951 | 17.682
Cost based on average annual cost per squadron
Total O&S Costs | Antecedent | ABC
Base Year $M | 102,995.2 | 184,011.9
Then Year $M | 245,665.3 | 395,147.2
Today
Product Support
13

## Slide 15: Program Schedule
F-35B & C
Integration
CTV
GTV
EMD
SDB-II
Development
Timeline*
CDR
PDR
SRR
1st AUR Avail
RISK REDUCTION
2 COMPETITIVE CONTRACTS
MS-B
F-15E Suite 7E OFP
DT IT OT
F-15E APG-70 GMTT
Dev & Test
F-15E
Integration
Normal attack
CAM/SAL
F-35 Block 3.X OFP
DT IT OT
F-35B
FISCAL YEAR
2012
2013
2014
2015
2016
2017
2018
2019
2020
2021
2022
2023
F-35C
JROC
AOA
1998-2000
To Complete
FY19-FY23
12,966
Normal Attack
OTRR
CAM/SAL
OTRR
F-35B & F-35C
OTRR
F-15E
RAA
F-15E
Full
Capability
F-15E
RAA
*Will be updated after
contract award
F-35B/C
Initial Fielding
2024
DT IT OT
BRU-61/A
Dual Power BRU-61/A
Delta Qual BRU-61/A for F-35 environment
MS-C
FRP
PRODUCTION
LRIP 1
LRIP 2
LRIP 3
LRIP 4
FRP 1
FRP 2
144
250
390
550
1050
Quantity
SVR
PCA
SVR
DT IT OT
83 mos
83 mos
59 mos
CA/Lot
Excerpt from 28 Jul 09 SDB II CDD, Cpt 11:
Required Assets Available (RAA): SDB II RAA is the capability to arm twelve (12) F-15Es with two (2) fully loaded BRU-61/A carriage systems each for 1.5 sorties (144 assets total)
DoN Assets for Initial Fielding: Initial quantity of SDB II weapons required is 90 weapons and 22 carriage systems based upon one ten (10) plane squadron with two (2) fully loaded carriage systems each plus ten spare weapons.
EOA
OA
IPR
Post-CDR
Report
Note: Due to delay of MS B, shaded blue region will move right accordingly
NEED TO ADD TOP LEVEL CRITICAL PATH
14
Notes: Identify Major Schedule Drivers:
Obsolescence?
Are we trying to beat someone in this competitive space, and what’s the value proposition for doing so?
What technical issues pace the project?
Note: Program schedule shall address critical path

## Slide 16: Program Schedule
FY13 FY14 FY15 FY16 FY17 FY18 FY19 FY20 FY21 FY22 FY23 FY24 FY25
Requirements
ICD
Acquisition
IOC
RIT
MDD
Annual
X-Plan
Milestones
AFRB
Requirements Review/Management Board
FDDR
Design & Integration
System/Architecture Studies
Contracting
Operations & Support
Test & Evaluation
OUE
OT&E
FOC
  Strategic & focused on Milestones and critical events between milestones. Must communicate schedule changes
Highlight critical path.
CA
Notes: Ensure that the critical path is highlighted
Identify critical events between milestones
Identify ADM requirements as necessary
Tailor schedule as necessary to identify cost, and/or schedule issues
Tailor schedule as necessary to reveal phases and/or increments of efforts
If event driven CSB, show integrated master schedule, highlighting issues
For pre-MDAP/MAIS programs, project a planned schedule
Must communicate schedule changes (include original date and the slipped date)
Consider to add Spectrum Supportability Risk Assessment Status and Equipment Spectrum Certification Stage impact on requirements. These have impacts on milestones, requirements and acquisition process.

## Slide 17: Program Schedule Assessment
Identify Major Schedule Drivers:
What technical issues pace the project?
Are we trying to beat someone in this competitive space, and what’s the likelihood for doing so?
  BBP 3.0 requires consideration of technology refresh plans in milestone and decision point reviews.
  Obsolescence?

## Slide 18: SAMPLE APT Framing Assumption #1
Expectations
Implications
Framing Assumption
Purpose-built will be competitive with existing designs
Basic aircraft and training system designs will be complete through vendor-conducted CDRs
Enter at MS B
Limited EMD of “deltas” to meet spec
PDR and competitive prototype waivers applicable*
Best-value source selection must consider risk
Contractor flight data to validate performance
Single step to full capability
Single award for EMD, Prod and ICS
RAA in 2023
FOC in 2031
*Air Force will still conduct comprehensive PDR and Critical Design Review (CDR) events post-contract award in support of Better Buying Power (BBP) 3.0 “Strengthen organic engineering capabilities” and SAF/AQ’s OTB Initiative.
“PRE-DECISIONAL – NOT FOR RELEASE”

## Slide 19: Sample APT Framing Assumption #2
Expectations
Implications
Framing Assumption
APT
requirements only
Mature technologies and systems available
Single step, limited EMD, waivers etc.
AETC sole customer
Separate PPBE
process for
other T-38 owners
Separate Planning Programming Budgeting and Execution (PPBE) process for APT derivative use capabilities
IOC 2023
“PRE-DECISIONAL – NOT FOR RELEASE”

## Slide 20: Alt Sample Framing Assumptions
Assumption* | Implications** | Expectations*** | Metric****
Design is Mature | Production concurrency possible | Schedule to IOC will be achieved | Schedule growth below historical median
Threat levels will not change much in the next 5 years | Capability changes unlikely | Costs to | 
Commercial demand will reduce unit cost | Production cost Est is realistic | No additional funding needed nor cost growth | 
See Notes pages for information
Notes: *The PM and team should develop the programs Framing Assumption and track the validity of the FAs by assessing relevant program metrics.
**Show implications, expectations and metrics for each key framing assumption. Thee should only be a few FAs (3-5); each should have these properties, cause major consequences, have no simple work-around, be uncertain at this point, be program specific (not generic, lie funding stability or good contractor performance ) and be a fundamental assumption that affect management decisions.
***Describe the visible expectations that flow from each implication of the FA.
****Specify metrics that can show whether these expectations are seen

## Slide 21: Program Org Chart
OSD/AT&L
SAF/AQ
PEO
Lt Gen JP Jones
PM
Col John Smith
Program
Control
Maj D. MacArthur
Contracts
Ms. Jane Smith
Sys Eng
Maj Kelly Johnson
Test
Maj C. Yeager
Test IPT
2 Captains
1 GS-12
5 Contractors
PC IPT
2 Captains
1 GS-12
5 Contractors
Contracts IPT
2 Captains
1 GS-12
Sys Eng IPT
2 Captains
1 GS-12
5 Contractors
ACC/A5XX
Col B Martin
OO-ALC/XYZ
Col Al Griggs
User
Depot
PSM
Lt. Col T. Jones
Support IPT
1 Captain
1 GS-12
4 Contractors
Consider to add SUPOCs.
Notes: Use existing program org charts so long as they show from MDA through PM and major IPTs within the program office.
In no case shall there be more than two levels of review between the Program Manager and the Milestone Decision Authority in accordance with DODD 5000.01, DODI 5000.02, and AFPD 63/20-1.
Include in your chart the Program Control Office, if you have one.

## Slide 22: DoD 5000.02 Tailoring Strategy
Discuss overall 5000.02 tailoring strategy
  Is program requesting approval for specific tailoring at this meeting?
  If not, why?
Discuss areas that have been tailored previously
Recommend area(s) that program intends to target for tailoring in future
Identify necessary dates & timelines to return for tailoring approval
Consider Spectrum Supportability Risk Assessment Status and Equipment Spectrum Certification Stage.

## Slide 23: Business Strategy
Competition Strategy
  How will competition be established and maintained through all phases of the acquisition (to include spares and depot repair) ?
  How does the competition strategy facilitate the acquisition strategy?
  What is the competition strategy for the upcoming acquisition phase?
  How do the results of the last acquisition phase impact the strategy for the upcoming phase?
  Provide results of your Business Case Analysis (performed in conjunction with the engineering tradeoff analysis to be presented at MS B, include intended use of MOSA)
  For Each Contract
  What is the purpose, type and value of the contract?
  How is the contract aligned with the acquisition and competition strategies?
  What is the incentive structure and how will the incentives foster contractor behavior resulting in favorable cost, schedule and performance outcomes?
  What criteria will be used to select the winning bidder? How do those criteria emphasize what is most important to the government?
  Will warranties be employed? How will they benefit the government?
  Does the contract anticipate the acquisition of technical data?
  Will the development utilize open systems architecture?
  Consider Spectrum Management language on contract, including all deliverables
21

## Slide 24: Program Funding
Notes: Notes:
+Enter values in the unshaded (white) annual and to-complete cells only. The rest of the data is calculated automatically. The spreadsheet cells will round to the nearest hundred thousand dollars ($0.1M).
+Delete any appropriation sections that have no budgeted or required costs.
+Programs must use footnotes to state source of "Required" estimate, O&S service life projection, O&S time horizon (first year of O&S – last year of O&S) & cost categories, and any RDT&E-funded quantities (if any). See Figure 1.
+Program offices are to use the latest version of the program funding template. Regularly check the Acquisition, Technology and Logistics (AT&L) Defense Acquisition Board (DAB) online calendar website (https://ebiz.acq.osd.mil/DABCalendar/) for the most current Integrated Product Team (IPT) Program Funding template. The template is updated as Programming, Planning, Budgeting, and Execution System (PPBES) events occur.
Definitions:
Primary Line Items: In the header of each section, list the primary budget line item(s) that fund the program currently and in the FYDP. For RDT&E, MILCON, and O&M, include appropriation (consistent with DAMIR reporting), budget activity and program element. For procurement, include appropriation, budget activity and line item. Some programs have smaller amounts of funding in secondary line items that need not be listed. Footnotes may be used for clarification/amplification.
Prior: President’s Budget (PB) position submitted prior to the Current budget position. Although the President only submits the FYDP to Congress, the cells for the next fiscal year and “To-Complete” should be populated for the investment appropriations using the values reported in the Selected Acquisition Report or latest DAES associated with that PB (if available).
Current: Latest approved Service POM/BES budget position or approved PB.
+During a normal PPBES cycle (PB submitted in the first Tuesday of February each year), use POM position from August through January; Use PB position from February through July.
+When the DoD Appropriation is enacted, programs should update that cell of all the "Current” PB funding and quantity rows to reflect the actual appropriated amounts.
Required: Latest estimate of funds required to successfully execute program, i.e., support the Warfighter and not simply match available budget Total Obligation Authorities (TOAs). Typically, this would reflect the Will Cost estimate, Service Cost Position (SCP), or PEO-supported Program Office Estimate (POE) that has not yet been validated by a Service Cost Agency or the CAPE. Note: total required quantity is the acquisition objective recognized by the Joint Requirements Oversight Council (JROC) or similar body and would be reflected in the program's Acquisition Program Baseline (APB) or similar document but may not be reflected in the budget due to affordability or funding issues.
System O&M: In this section, list the O&M-funded costs from initial system deployment through end of system operations. Include all costs of operating, maintaining, and supporting a fielded system. Specifically, this consists of the costs (organic and contractor) of equipment, supplies, software, and services associated with operating, modifying, maintaining, supplying, training, and supporting a system in the DoD inventory. Do not include acquisition-related O&M, and non-O&M O&S costs such as military personnel, and investment-funded system improvements. Also, do not include disposal costs, which represent a separate phase of the program life cycle. Please address questions on the O&M requirements to the OSD(AT&L)/L&MR point of contact listed below.
Total Required Acquisition (BYXX$M):
+Current Estimate of Total RDT&E, procurement, MILCON and acquisition-related O&M in base-year dollars as reported in the program's latest approved POM budget position, approved PB, or quarterly DAES submission, whichever is most current.
+The percentage displayed is the portion of the Acquisition cost out of the sum of Acquisition and O&S costs.
+Revise “BYXX$M” to reflect the 2-digit program Base Year (e.g., BY16$M). Use the Base Year specified in the current Acquisition Program Baseline (APB). For unbaselined programs (or if seeking a new or revised APB), use the budget year (e.g., BY18$M for PB18).
Total Required O&S (BYXX$M):
+Current Estimate of Total Operating and Support costs in base-year dollars as reported in the program’s quarterly DAES (if applicable). See Figure 2.
+A footnote should identify the projected service life.
+Disposal costs should not be included in this value.
+The percentage displayed is the portion of the O&S cost out of the sum of Acquisition and O&S costs. This value should not include disposal dollars.
+Revise “BYXX$M” to reflect the 2-digit program Base Year (e.g., BY16$M, IAW the instructions above for Total Required Acquisition).
Curr Est (APUC): Program Manager’s current estimate of Average Procurement Unit Cost, in base-year dollars (total procurement divided by procurement-funded quantities). The APUC should match the values reported in the program's latest approved POM/BES budget position, approved PB, or quarterly DAES submission, whichever is most current.
Curr Est (PAUC): Program Manager’s current estimate of Program Acquisition Unit Cost, in base-year dollars (total RDT&E, procurement, MILCON and acquisition-related O&M divided by total quantity). The PAUC should match the values reported in the program's latest approved POM/BES budget position, approved PB, or quarterly DAES submission, whichever is most current.
Δ Current: This is the program’s APUC or PAUC current estimate (as defined above) divided by the program’s current APB Unit Cost Reporting (UCR) baseline, as applicable. Figure 3 illustrates where this information resides in the program’s DAMIR DAES.
Δ Original: This is the program’s APUC or PAUC current estimate (as defined above) divided by the program’s original APB UCR baseline, as applicable. See Figure 3.
Points of Contact:
Army Programs:
Allen Johnson, OSD(AT&L)/ARA
allen.m.johnson44.ctr@mail.mil
703-697-5384
Navy Programs:
CDR Joseph Mitzen, OSD(AT&L)/ARA
joseph.b.mitzen.mil@mail.mil
703-697-8020
Air Force Programs: Matthias Maier, OSD(AT&L)/ARA matthias.r.maier.ctr@mail.mil 703-614-4030
Agency & Department-wide Programs:
Mr. Russ Vogel, OSD(AT&L)/ARA
russell.a.vogel.civ@mail.mil
703-697-1786
O&S Section:
Ms. Molly Mertz, OSD(AT&L)/L&MR
mary.m.mertz.civ@mail.mil
703-614-6137

## Slide 25
Likelihood
Consequence
Bell Supply Chain Management to Support Increase to Full Rate Production
Driver: Poor performance of key suppliers, long lead times (bearings, forgings, castings), LLT purchase orders, staffing, parts shortages, and limited capacity in critical suppliers
Mitigation Plan:
Obtain Advanced Procurement in FY10
Hire Govt Supply Chain Manager (V-22)
Identify dual source for critical suppliers
Rationalize supply base
Place Bell reps on-site at critical suppliers
Hire staffing to meet demand
Utilize Bell gated process for outsourcing
Award FY10 Long Lead
Support Prime key supplier visits with government representation
Production Readiness Review (support FRP decision)
Date: COMPLETE Jul 10 (Risk will be closed/deleted next quarter)
Ability to Achieve Affordability Targets to Meet Inventory Objectives
Driver: Higher than anticipated costs due to Bell enterprise growth (overhead rates); raw materials; cabin; supplier performance; increased labor hours. Two rate increases, Apr Forward Price Rate Agreement and Nov Forward Price Rate Brochure (driven by a reduction in the base vs. predictions, erosion in the commercial business, efficiencies in production, a recent strike, and pension liabilities) have recently created additional budget pressure.
Mitigation Plan:
Establish Affordability plan
Implement GFE CRIs (Engines, OTO)
Obtain Advanced Procurement in FY10
Execute Long Term Agreements/Long Term Contracts
Finalize SOF inspection requirements
Implement cost growth control and cost reduction initiatives
Assess impacts of PB11 Budget and rate increases with Lot 7 Production Proposal
Include spares in production contract
Complete Business Case Analysis for MYP
If supported by BCA, ensure MYP budget approval/lay-in and implement MYP to begin in FY14
Date: On-going
Failure to Meet Total Ownership Cost Reduction Goals
Driver: Delayed I and D level standup, dynamic component DL&T disposition, extended ICS, components not making reliability targets
Mitigation Plan:
Conduct BCA for long term logistics sustainment/PBL strategy
Stand up Organic Intermediate and Depot Level repair
NAVAIR approval of H-1 DL&T’s
Execute 5 year Interim Support Plan contract awards
CILR drives component redesign efforts/BCAs
Date: Ongoing
Insufficient funding to execute aircraft quantity requirements
Driver: Two Forward Price Rate Agreement (FPRA) increases, Apr FPRA and Nov FPR Recommendation (driven by a reduction in the base vs. predictions, erosion in the commercial business, efficiencies in production, a recent strike, and pension liabilities) and potential additional rate impacts due to Pension Protection Act compliance and projected business base loss in FY14 due to decreasing procurement of V-22s are creating additional budget pressure to execute yearly budgeted a/c quantities and pressurizing APB and Nunn-McCurdy acquisition thresholds.
Mitigation Plan:
Finalize technical evaluation and negotiation of the lot 7 contract {Leadership intervention as required}
Assess potential future rate increases and impacts on budget across program fiscal years (ongoing)
  Pension Protection Act assessment (AIR 4.2 Lead)
  Business base (DCMA lead)
Continue to Pursue cost reduction/control initiatives (ongoing; see affordability risk)
Update program manager’s cost estimate
Engage Service for funding resolution
Support PEO(A)/DCMA rate control initiative with Bell (ongoing)
Date: Oct 10 (AH-1Z FRP decision)
Program Risks
Notes: 25
25
Ensure that you consider intelligence impacts as an area for risk to program.
  The DoDI 5000.0-2 requires a demonstration for MS B that all sources of risk have been adequately mitigated to support a commitment to design for production. This includes technology, engineering, integration, manufacturing, sustainment, and cost risks

## Slide 26: MS B Document Status
Documentation | S/R* | Status | Comments
2366b Certification | S | In OSD Coord | 
Acquisition Decision Memorandum (ADM) | R | In draft form | 
Acquisition Program Baseline (APB) | S/R | In-Work | Program Office will finalize after AFCAA
Acquisition Strategy (update) | S/R | Complete | 
Affordability Cap (Analysis) | R | In Coord | In SAF 3-ltr Coord
Bandwidth Requirements Review (update) | S/R | Final | .
Clinger-Cohen Act Compliance | S | In-Work | To be completed prior to MS B DAB
Component Cost Estimate | R | Complete | To be completed NLT 30 June (AFCAA coordinating with CAPE)
Component Cost Position | R | Complete | 
Core Logistics Determination | S | Complete | 
Low-rate Initial Production Quantity | S |  | 
Cost Analysis Requirements Description (CARD) | R | In-work | 
Complete | On-Track | Minor Issues | Major Issues
* S=Statutory, R=Regulatory
PMs will address their streamlining documentation strategy

## Slide 27: MS B Document Status
Documentation | S/R* | Status | Comments
Economic Analysis (MAIS Statutory) | S | In-Work | 
Exit Criteria | R | In-work | 
Frequency Allocation Application (DD 1494) | S | Final | 
Full Funding Certification Memo | R | Final | 
Independent Cost Estimate | S | Final | 
Independent Logistics Assessment | S | On-track | 
Information Support Plan Bandwidth Requirements Review | R/S | In-Work | 
Life Cycle Mission Data Plan | R | Finished | 
Life Cycle Sustainment Plan Core Logistics Determination | R |  | 
Manpower Estimate | S | Complete | 
PESCHE and NEPA Compliance schedule | S | On-track | Awaiting AQD coordination
* S=Statutory, R=Regulatory
Complete | On-Track | Minor Issues | Major Issues
PMs will address their streamlining documentation strategy

## Slide 28: MS B Document Status
Documentation | S/R* | Status | Comments
Program Certification to DBS Mgt Committee | S | Complete | 
Program Protection Plan Cyber Security Strategy | S | Complete | 
Replaced System Sustainment Plan | S | Complete | 
Spectrum Supportability Risk Assessment | R |  | 
Systems Engineering Plan (Update) Item Unique ID implementation Plan Corrosion Prevention Control Plan (Update) | R | In-Work | In work to finalize 30 May.
Technology Readiness Assessment (as applicable) | S | Final | 
Test & Evaluation Master Plan (update) | R | In-work | In final coordination at DOT&E
Waveform Assessment Application | R | Final | PEO signed 14 May
* S=Statutory, R=Regulatory
Complete | On-Track | Minor Issues | Major Issues
PMs will address their streamlining documentation strategy

## Slide 29: ADM Proposed Language
Proposed Acquisition Decision Memorandum Language:
I have made the certifications required by section 2366b of title 10, United States Code
I approve the Acquisition Program Baseline (APB)
I approve MS B and authorize entrance into Engineering and Manufacturing Development (EMD)
Affordability Cap is $ (see notes page)
EMD proposed Exit Criteria
  XXX
  YYY
  ZZZ
Notes: Two Caps--Average Procurement Unit Cost and lifetime average Operating an Support Cost per annum. See Affordability Enclosure 8 for DOD I 5000.02, 26 November 2013.
Sample from another program: Current Affordability Caps
  Average Procurement Unit Cost (APUC)
    Program Office Estimate APUC (Sep 13) = $31.8M (TY$M)
    Development RFP Release ADM APUC (Nov 13) = ~$36.6M (TY$M)
  Operations & Support (O&S) Costs
    Program Office Estimate O&S per unit, per year (Sep 13) = $3.6M (TY$M)
    Development RFP Release O&S per unit, per year (Nov 13) = ~$3.9M (TY$M)

## Slide 30: Way Ahead
Awaiting OSD approval of APB
OIPT scheduled for XX Date
DAB scheduled for XXX Date

## Slide 31
BACKUP and SAMPLES
See Footnotes for additional information
Notes: International Cooperation, Systems Assessment and the other topics included in Back-up should be moved forward to the basic briefing when they are a “key part” that needs to be addressed in the Briefing. BUT keep in mind the 1 hour limit to the briefing.

## Slide 32
Cooperative Activities: (list cooperative partners, describe cooperative participation in the program, both current and planned, to include list of actual international agreements-- e.g., bilateral or multilateral discussions, loans of equipment, information exchanges, cooperative RDT&E, co-production DEA/IEAs in technology area, etc.)
Foreign sales: (list current or potential FMS or Direct Commercial Sales buyers)
Interoperability Requirements: (list all international objective and threshold requirements in program documents (JCIDS and 5000 series); describe plan to achieve those requirements, to include which increment of a program they will be achieved)
Foreign technology assessment: (from TDS and AoA; guidance in Deskbook Acquisition Guidebook, Section 2.3.6., identify how 10USC2350a statutory requirement has been met; assessment whether or not a project similar capability is in development or production in a partner nation that could be procured or modified to meet DoD needs)
(Identify issues specific to international -- e.g., impact (cost, schedule, performance) of proposed cuts on partner(s)/buyer(s), updated APUC, status of negotiations and impact to US and partners under the relevant agreement(s) (MOU, MOA, LOA)
Key Technologies: (description of the technologies and CPI in the program)
Anti-Tamper Analysis: (based on ATEA Guidance and Defense Exportability assessment)
Differential Capability Analysis: (Assess potential need for development of differential capabilities for a range of anticipated coalition partners in view of the interoperability requirements, cooperative activities, and potential foreign sales efforts envisioned)
Proposed Approach: (Describe how design and development of validated AT and Differential Capability requirements will be addressed in the program’s master schedule )
Choose appropriate funding chart below
*-from Spruill chart

## Slide 33
Milestone Exit Criteria

## Slide 34: Milestone B – Required Documents
2366b Certification Memorandum ARA ARA MDA
Acquisition Decision Memorandum (ADM) OIPT Lead/ARA ARA MDA
Acquisition Program Baseline (APB) Component ARA MDA
Acquisition Strategy Component ARA MDA
Affordability Cap (Analysis) Component OIPT Lead/ARA/CAPE MDA
Bandwidth Requirements Review Component DoD CIO DOD CIO
Clinger-Cohen Act Compliance Component CIO AF CIO
Component Cost Estimate Component CAPE Component
Component Cost Position Component CAPE Component
Core Logistics Determination Component LM&R Component
Cost Analysis Requirements Description (CARD) Component CAPE Component
Cybersecurity Strategy Component CIO DOD/AF CIO Review
Economic Analysis (MAIS statutory) Component AF CIO Component
Exit Criteria Component ARA MDA
Frequency Allocation Application (DD1494) Component DOD CIO NT and IA
Full Funding Certification Memo Component ARA/CAPE/Comp MDA/CAPE
Independent Cost Estimate CAPE DCAPE DCAPE
Independent Logistics Assessment Component OASD(L&MR)/DASD(MR) CAE
Information Support Plan Component CIO AF CIO
  Bandwidth Requirements Review Component DOC CIO DOD CIO
Document Originator OSD OPR* Approver
PMs will address their streamlining documentation strategy
Notes: Not all document requirements are required for all programs. See DOD I 5000.02, Enclosure 1 for details

## Slide 35
Requirement Cost Driver (i.e. KPP, KSA, other attributes) | Proposed Relaxed Requirements | Operational Risk/Impact | Reduced System Capability | Change in Cost (e.g. LCCE, APUC, RDT&E, Production, O&S, etc.)
KPP 1 : Radar System Performance | Increase search update interval by 5 seconds | Reduces TBM growth capability | Req’d power aperture decreased by 15% | $50M reduction in RDT&E
KPP 2: Sustainment Material Availability | Relax from 64% to 50% | Possibly unable to meet optimum 36mo. maintenance cycles so as to maintain Mission Readiness | Req 2 new aircraft instead of 3 | $9B reduction in LCCE
KPP 3: Mission Execution (Comm) | Partially enable wireless communication | Unable to provide full C3 capability – reduce responsiveness | Integrate with only basic wireless capability | $10M reduction in RDT&E
Cost Driver/Operational Requirements
Trade space
See notes
Notes: This chart is intended to help the program generate ideas for potential tradeoffs. Data may or may not be available depending on the timing of the Milestone. The table includes operational requirements that are potential tradeoffs and the associated operational and cost impact of the trade. The table includes the KPPs, KSAs, and APAs that are the primary cost and schedule drivers.