## POAM for ICD DCR
Step | Event | # Days | Estimated Date | Actual Date | Notes:
1 | Sponsor's Requirement Office submits SPR Request to AF/A5DR via IRSS. Additionally, Sponsor's Requirement Office O-6 sends email to AFGK with SPR Request. |  | 2024-04-19 |  | Enter anticipated date for completion of Step 1 in the highlighted cell.
2 | AF/A5DR conducts Pre-AFGK Review of SPR Worksheet, POAM, and other support materials | 7 | 2024-04-26
3 | SPR Chair convenes SPR; approves Solution Pathway | 0 | 2024-04-26 |  | Enter date of the SPR. The Estimated Date cells should auto-populate
4 | Sponsor takes corrective actions as directed by SPR Chair; convenes Document Writing Event | 14 | 2024-05-10
5 | Sponsor concludes Document Writing Event | 7 | 2024-05-17
6 | Sponsor conducts Post Event Activities; submits Initial Staffing Request to AF/A5DR via IRSS Task | 28 | 2024-06-14 |  | Enter anticipated Document submission date. The Estimated Date cells should auto-populate
7 | AF/A5DR conducts Pre-AFGK Review; A5D approves Initial Staffing | 7 | 2024-06-21
8 | AF/A5DR intiates Initial Staffing in IRSS; submits Document to JS Gatekeeper for review | 0 | 2024-06-21
9 | JS Gatekeeper submits Document for Commenting in KM/DS | 4 | 2024-06-25
10 | JS Gatekeeper closes Commenting in KM/DS | 14 | 2024-07-09
11 | AF/A5DR closes Initial Staffing in IRSS | 0 | 2024-07-09
12 | AF/A5DR submits Comment Resolution Task to Sponsor via IRSS | 0 | 2024-07-09
13 | Sponsor resolves comments; submits eAFROC Coordination Request to AF/A5DR via IRSS | 21 | 2024-07-30
14 | AF/A5DR conducts Pre-AFGK Review; A5D approves eAFROC Coordination | 7 | 2024-08-06
15 | AF/A5DR initiates eAFROC Coordination | 0 | 2024-08-06
16 | AF/A5DR closes eAFROC Coordination | 14 | 2024-08-20
17 | AF/A5DR submits eAFROC Comment Adjudication Task to Sponsor | 0 | 2024-08-20
18 | Sponsor adjudicates eAFROC Comments; provides updated documents, as required | 7 | 2024-08-27
19 | AF/A5DR staffs AFRDM for RDA Signature | 0 | 2024-08-27
20 | AF/A5D coordinates/signs AFRDM; Sponsor cleared to attend FCB WG/FCB | 14 | 2024-09-10
21 | AF/A57 signs SSS for AFRDM Staff Package | 7 | 2024-09-17
22 | CSAF signs AFRDM; Sponsor cleared to attend JCB | 14 | 2024-10-01
23 | Sponsor takes Document to JROC; obtains JROCM | 14 | 2024-10-15
Formulas:
Estimated Date = [Estimated Date, row above]+C3

## POAM for IS-ICD
Step | Event | # Days | Estimated Date | Actual Date | Notes:
1 | Sponsor's Requirement Office submits SPR Request to AF/A5DR via IRSS. Additionally, Sponsor's Requirement Office O-6 sends email to AFGK with SPR Request. |  | 2024-04-19 |  | Enter anticipated date for completion of Step 1 in the highlighted cell.
2 | AF/A5DR conducts Pre-AFGK Review of SPR Worksheet, POAM, and other support materials | 7 | 2024-04-26
3 | SPR Chair convenes SPR; approves Solution Pathway | 0 | 2024-04-26 |  | Enter date of the SPR. The Estimated Date cells should auto-populate
4 | Sponsor takes corrective actions as directed by SPR Chair; convenes Document Writing Event | 14 | 2024-05-10
5 | Sponsor concludes Document Writing Event | 7 | 2024-05-17
6 | Sponsor conducts Post Event Activities; submits Initial Staffing Request to AF/A5DR via IRSS Task | 28 | 2024-06-14 |  | Enter anticipated Document submission date. The Estimated Date cells should auto-populate
7 | AF/A5DR conducts Pre-AFGK Review; A5D approves Initial Staffing | 7 | 2024-06-21
8 | AF/A5DR intiates Initial Staffing in IRSS; submits Document to JS Gatekeeper for review | 0 | 2024-06-21
9 | JS Gatekeeper submits Document for Commenting in KM/DS | 3 | 2024-06-24
10 | JS Gatekeeper closes Commenting in KM/DS | 14 | 2024-07-08
11 | AF/A5DR closes Initial Staffing in IRSS | 0 | 2024-07-08
12 | AF/A5DR submits Comment Resolution Task to Sponsor via IRSS | 0 | 2024-07-08
13 | Sponsor resolves comments; submits eAFROC Coordination Request to AF/A5DR via IRSS | 14 | 2024-07-22
14 | AF/A5DR conducts Pre-AFGK Review; A5D approves eAFROC Coordination | 7 | 2024-07-29
15 | AF/A5DR initiates eAFROC Coordination | 0 | 2024-07-29
16 | AF/A5DR closes eAFROC Coordination | 14 | 2024-08-12
17 | AF/A5DR submits eAFROC Comment Adjudication Task to Sponsor | 0 | 2024-08-12
18 | Sponsor adjudicates eAFROC Comments; provides updated documents, as required | 7 | 2024-08-19
19 | AF/A5DR staffs AFRDM for RDA Signature | 0 | 2024-08-19
20 | AF/A5D coordinates/signs AFRDM; Sponsor cleared to attend FCB WG/FCB | 14 | 2024-09-02
21 | AF/A57 signs SSS for AFRDM Staff Package | 7 | 2024-09-09
22 | CSAF signs AFRDM; Sponsor cleared to attend JCB | 14 | 2024-09-23
23 | Sponsor takes Document to JROC; obtains JROCM | 14 | 2024-10-07
Formulas:
Estimated Date = [Estimated Date, row above]+C3

## POAM for CDD IS-CDD
Step | Event | # Days | Estimated Date | Actual Date | Notes:
1 | Sponsor's Requirement Office submits SPR Request to AF/A5DR via IRSS. Additionally, Sponsor's Requirement Office O-6 sends email to AFGK with SPR Request. |  | 2024-04-19 |  | Enter anticipated date for completion of Step 1 in the highlighted cell.
2 | AF/A5DR conducts Pre-AFGK Review of SPR Worksheet, POAM, and other support materials | 7 | 2024-04-26
3 | SPR Chair convenes SPR; approves Solution Pathway | 0 | 2024-04-26 |  | Enter date of the SPR. The Estimated Date cells should auto-populate
4 | Sponsor takes corrective actions as directed by SPR Chair; convenes Document Writing Event | 14 | 2024-05-10
5 | Sponsor concludes Document Writing Event | 7 | 2024-05-17
6 | Sponsor conducts Post Event Activities; submits Initial Staffing Request to AF/A5DR via IRSS Task | 28 | 2024-06-14 |  | Enter anticipated Document submission date. The Estimated Date cells should auto-populate
7 | AF/A5DR conducts Pre-AFGK Review; A5D approves Initial Staffing | 7 | 2024-06-21
8 | AF/A5DR intiates Initial Staffing in IRSS; submits Document to JS Gatekeeper for review | 0 | 2024-06-21
9 | JS Gatekeeper submits Document for Commenting in KM/DS | 10 | 2024-07-01
10 | JS Gatekeeper closes Commenting in KM/DS | 21 | 2024-07-22
11 | AF/A5DR closes Initial Staffing in IRSS | 0 | 2024-07-22
12 | AF/A5DR submits Comment Resolution Task to Sponsor via IRSS | 0 | 2024-07-22
13 | Sponsor resolves comments; submits eAFROC Coordination Request to AF/A5DR via IRSS | 30 | 2024-08-21
14 | AF/A5DR conducts Pre-AFGK Review; A5D approves eAFROC Coordination | 7 | 2024-08-28
15 | AF/A5DR initiates eAFROC Coordination | 0 | 2024-08-28
16 | AF/A5DR closes eAFROC Coordination | 14 | 2024-09-11
17 | AF/A5DR submits eAFROC Comment Adjudication Task to Sponsor | 0 | 2024-09-11
18 | Sponsor adjudicates eAFROC Comments; provides updated documents, as required | 7 | 2024-09-18
19 | AF/A5DR staffs AFRDM for RDA Signature | 0 | 2024-09-18
20 | AF/A5D coordinates/signs AFRDM; Sponsor cleared to attend FCB WG/FCB | 14 | 2024-10-02
21 | AF/A57 signs SSS for AFRDM Staff Package | 7 | 2024-10-09
22 | CSAF signs AFRDM; Sponsor cleared to attend JCB | 14 | 2024-10-23
23 | Sponsor takes Document to JROC; obtains JROCM | 14 | 2024-11-06
Formulas:
Estimated Date = [Estimated Date, row above]+C3

## POAM for SW-ICD
Step | Event | # Days | Estimated Date | Actual Date | Notes:
1 | Sponsor's Requirement Office submits SPR Request to AF/A5DR via IRSS. Additionally, Sponsor's Requirement Office O-6 sends email to AFGK with SPR Request. |  | 2024-04-19 |  | Enter anticipated date for completion of Step 1 in the highlighted cell.
2 | AF/A5DR conducts Pre-AFGK Review of SPR Worksheet, POAM, and other support materials | 7 | 2024-04-26
3 | SPR Chair convenes SPR; approves Solution Pathway | 0 | 2024-04-26 |  | Enter date of the SPR. The Estimated Date cells should auto-populate
4 | Sponsor takes corrective actions as directed by SPR Chair; convenes Document Writing Event | 14 | 2024-05-10
5 | Sponsor concludes Document Writing Event | 7 | 2024-05-17
6 | Sponsor conducts Post Event Activities; submits eAFROC Rapid Staffing Request to AF/A5DR via IRSS Task | 28 | 2024-06-14 |  | Enter anticipated Document submission date. The Estimated Date cells should auto-populate
7 | AF/A5DR conducts Pre-AFGK Review; A5D approves eAFROC Rapid Staffing | 7 | 2024-06-21
8 | AF/A5DR intiates eAFROC Rapid Staffing in IRSS; submits Document to JS Gatekeeper for review | 0 | 2024-06-21
9 | JS Gatekeeper submits Document for Commenting in KM/DS | 2 | 2024-06-23
10 | JS Gatekeeper closes Commenting in KM/DS | 10 | 2024-07-03
11 | AF/A5DR closes eAFROC Rapid Staffing in IRSS | 0 | 2024-07-03
12 | AF/A5DR submits Comment Resolution Task to Sponsor via IRSS | 0 | 2024-07-03
13 | Sponsor adjudicates Comments; provides updated documents, as required | 10 | 2024-07-13
14 | AF/A5DR staffs AFRDM for RDA Signature | 0 | 2024-07-13
15 | AF/A5D coordinates/signs AFRDM; Sponsor cleared to attend FCB WG/FCB | 14 | 2024-07-27
16 | AF/A57 signs SSS for AFRDM Staff Package | 7 | 2024-08-03
17 | CSAF signs AFRDM; Sponsor cleared to attend JCB | 8 | 2024-08-11
18 | Sponsor takes Document to JROC; obtains JROCM | 8 | 2024-08-19
Formulas:
Estimated Date = [Estimated Date, row above]+C3